# Applied Software Project Management

Estimation

What is estimation?

The project manager must set expectations about the time required to complete the software among the stakeholders, the team, and the organization’s management.

If those expectations are not realistic from the beginning of the project, the stakeholders will not trust the team or the project manager.

# Elements of a Sound Estimate

To generate a sound estimate, a project manager must have:

wA work breakdown structure (WBS), or a list of tasks which, if completed, will produce the final product

wAn effort estimate for each task

wA list of assumptions which were necessary for

making the estimate

wConsensus among the project team that the estimate is accurate

## Assumptions Make Estimates More Accurate

Team members make assumptions about the work to be done in order to deal with incomplete information

wAny time an estimate must be based on a decision

that has not yet been made, team members can assume the answer for the sake of the estimate

wAssumptions must be written down so that if they prove to be incorrect and cause the estimate to be inaccurate, everyone understands what happened

wAssumptions bring the team together very early on

in the project so they can make progress on important decisions that will affect development

# Wideband Delphi

Wideband Delphi is a process that a team can use to generate an estimate wThe project manager chooses an

estimation team, and gains consensus among that team on the results

wWideband Delphi is a repeatable

estimation process because it consists of a straightforward set of steps that can be performed the same way each time

# The Wideband Delphi Process

Step 1: Choose the team wThe project manager selects the estimation team and a moderator. The team should consist of 3 to 7 project team members.

- The moderator should be familiar with the Delphi process, but should not have a stake in the outcome of the session if possible.

- If possible, the project manager should not be the moderator because he should ideally be part of the estimation team.

# The Wideband Delphi Process

Step 2: Kickoff Meeting wThe project manager must make sure that each team member understands the Delphi process, has read the vision and scope document and any other documentation, and is familiar with the project background and needs.

wThe team brainstorms and writes down assumptions.

wThe team generates a WBS with 10-20 tasks. wThe team agrees on a unit of estimation.

# The Wideband Delphi Process

Step 3: Individual Preparation wEach team member independently

generates a set of preparation results. wFor each task, the team member writes

down an estimate for the effort required to complete the task, and any additional assumptions he needed to make in order to generate the estimate.

# The Wideband Delphi Process

Step 4: Estimation Session wDuring the estimation session, the team comes to a consensus on the effort required for each task in the WBS.

wEach team member fills out an estimation form which contains his estimates.

wThe rest of the estimation session is divided into rounds during which each estimation team member revises her estimates based on a group discussion. Individual numbers are not dicsussed.

# The Wideband Delphi Process

Step 4: Estimation Session (continued) wThe moderator collects the estimation forms and plots the sum of the effort from each form on a line:

# The Wideband Delphi Process

Step 4: Estimation Session (continued) w The team resolves any issues or disagreements that are brought up.

• Individual estimate times are not discussed. These disagreements are usually about the tasks themselves. Disagreements are often resolved by adding assumptions.

w The estimators all revise their individual estimates. The moderator updates the plot with the new total:

# The Wideband Delphi Process

Step 4: Estimation Session (continued):

- The moderator leads the team through several rounds of estimates to gain consensus on the estimates. The estimation session continues until the estimates converge or the team is unwilling to revise estimates.

Step 5: Assemble Tasks

- The project manager works with the team to collect the estimates from the team members at the end of the meeting and compiles the final task list, estimates and assumptions.

Step 6: Review Results

- The project manager reviews the final task list with the estimation team.

# Other Estimation Techniques

PROBE, or Proxy Based Estimating

- PROBE is based on the idea that if an engineer is building a component similar to one he built previously, then it will take about the same effort as it did in the past.

- Individual engineers use a database to maintain a history of the effort they have put into their past projects.

- A formula based on linear regression is used to calculate the estimate for each task from this history.

COCOMO II

- In Constructive Cost Model, or COCOMO, projects are summarized using a set of variables that must be provided as input for a model that is based on the results of a large number of projects across the industry.

- The output of the model is a set of size and effort estimates that can be developed into a project schedule.

# Other Estimation Techniques

The Planning Game

- The Planning Game is the software project planning method from Extreme Programming (XP), a lightweight development methodology developed by Kent Beck in the 1990s at Chrysler.

- It is a full planning process that combines estimation with identifying the scope of the project and the tasks required to complete the software.

- The Planning Game is highly iterative. The scope is established by having Development and Business work together to interactively write “user stories” written on index cards to describe the scope. Each story is given an estimate of 1, 2 or 3 weeks. This process is repeated continuously throughout the project.

1️⃣ Khái niệm về ước lượng (What is Estimation)

- Ước lượng là việc xác định bao nhiêu thời gian và công sức cần để hoàn thành phần mềm.

- Mục tiêu của người quản lý dự án là thiết lập kỳ vọng thực tế cho:

  - Bên liên quan (stakeholders)

  - Đội ngũ phát triển (team)

  - Ban lãnh đạo công ty (management)

- Nếu ngay từ đầu ước lượng không thực tế, các bên sẽ mất niềm tin vào người quản lý và đội phát triển.

👉 Tóm lại: Ước lượng không chỉ là con số, mà là công cụ xây dựng niềm tin.

2️⃣ Các yếu tố tạo nên ước lượng chính xác (Elements of a Sound Estimate)

Một bản ước lượng “vững chắc” cần có 4 yếu tố:

- Work Breakdown Structure (WBS)
→ Danh sách chi tiết các công việc phải làm để tạo ra sản phẩm cuối cùng.
→ Ví dụ: “Thiết kế giao diện”, “Viết API”, “Kiểm thử người dùng”...

- Effort Estimate cho từng nhiệm vụ
→ Mỗi nhiệm vụ cần có ước lượng công sức (effort) riêng (tính theo giờ, ngày hoặc tuần).

- Assumptions (Giả định)
→ Ghi lại các giả định được đưa ra khi ước lượng, ví dụ:

  - “Có sẵn dữ liệu mẫu.”

  - “Team đã quen với công nghệ này.”
→ Nếu giả định sai, ta biết nguyên nhân ước lượng lệch.

- Consensus (Đồng thuận nhóm)
→ Toàn bộ nhóm thống nhất rằng ước lượng là hợp lý và có thể đạt được.

3️⃣ Giả định giúp ước lượng chính xác hơn (Assumptions Make Estimates More Accurate)

- Trong thực tế, nhiều thông tin còn thiếu khi bắt đầu ước lượng.

- Vì vậy, nhóm phải đưa ra giả định tạm thời để có thể tiến hành.

- Những giả định đó phải được ghi rõ trong tài liệu để sau này nếu sai, mọi người hiểu lý do.

- Việc thảo luận giả định còn giúp nhóm hiểu rõ dự án và thống nhất hướng phát triển sớm.

4️⃣ Quy trình Wideband Delphi (The Wideband Delphi Process)

Đây là phương pháp ước lượng theo nhóm được sử dụng phổ biến vì dễ áp dụng và chính xác.
Nó dựa trên việc thu thập ý kiến độc lập từ nhiều chuyên gia, rồi thống nhất kết quả cuối cùng.

6 Bước của Wideband Delphi:

- Chọn nhóm (Choose the team)

  - Project Manager chọn 3–7 người tham gia + 1 người điều phối (moderator).

  - Moderator nên là người không có quyền lợi trực tiếp trong kết quả.

  - PM có thể tham gia ước lượng, nhưng không nên làm moderator.

- Họp khởi động (Kickoff Meeting)

  - Tất cả thành viên hiểu mục tiêu dự án và quy trình Delphi.

  - Cùng nhau brainstorm các giả định.

  - Xây dựng WBS khoảng 10–20 nhiệm vụ.

  - Thống nhất đơn vị ước lượng (ví dụ: giờ, ngày).

- Chuẩn bị cá nhân (Individual Preparation)

  - Mỗi thành viên tự ước lượng riêng cho từng nhiệm vụ, không trao đổi với người khác.

  - Ghi lại ước lượng và giả định cá nhân.

- Phiên họp ước lượng (Estimation Session)

  - Cả nhóm cùng thảo luận nhưng không nói con số cụ thể của nhau.

  - Mỗi người nộp “form ước lượng”.

  - Moderator tổng hợp kết quả, vẽ biểu đồ so sánh.

  - Mọi người thảo luận sự khác biệt, thường là do hiểu nhiệm vụ khác nhau.

  - Có thể thêm giả định mới cho rõ ràng hơn.

- Tổng hợp kết quả (Assemble Tasks)

  - Project Manager thu thập toàn bộ form ước lượng,
tổng hợp thành danh sách nhiệm vụ, giả định, và công sức trung bình.

- Rà soát kết quả (Review Results)

  - Cả nhóm xem lại danh sách cuối cùng để đảm bảo mọi người đồng thuận với ước lượng.

👉 Ưu điểm: quy trình tập thể, minh bạch, dễ lặp lại và cho ra kết quả thực tế nhất.

5️⃣ Các kỹ thuật ước lượng khác (Other Estimation Techniques)

A. PROBE (Proxy-Based Estimating)

- Dựa trên ý tưởng:
“Nếu kỹ sư từng xây một thành phần tương tự trước đây, thì công sức cũng sẽ gần giống.”

- Mỗi kỹ sư duy trì cơ sở dữ liệu lịch sử cá nhân về các dự án cũ.

- Sử dụng hồi quy tuyến tính (linear regression) để tính công sức trung bình cho công việc mới.

B. COCOMO II (Constructive Cost Model)

- Mô hình ước lượng dựa trên dữ liệu từ nhiều dự án trong ngành.

- Người dùng nhập vào các biến như:

  - Kích thước phần mềm (LOC, Function Points)

  - Độ phức tạp

  - Kinh nghiệm nhóm

  - Ràng buộc thời gian

- Mô hình xuất ra ước lượng về quy mô, công sức và thời gian.

- Thường dùng để xây dựng lịch trình chi tiết (project schedule).

C. The Planning Game (Extreme Programming – XP)

- Kỹ thuật ước lượng linh hoạt và lặp lại (iterative) của phương pháp XP.

- Nhóm phát triển và khách hàng cùng nhau:

  - Viết user stories lên thẻ (index cards).

  - Mỗi story được ước lượng 1, 2 hoặc 3 tuần.

  - Khi có thay đổi, lặp lại quy trình ước lượng.

Giúp dự án thích nghi nhanh với thay đổi yêu cầu