Applied Software Project Management

Introduction

Why do software projects fail?

People begin programming before they understand the problem

Everyone likes to feel that they’re making progress

When the team starts to code as soon as the project begins, they see immediate gains

When problems become more complex (as they always do!), the work gets bogged down

In the best case, a team that begins programming too soon will end up writing good software that solves the wrong problem

Why do software projects fail?

The team has an unrealistic idea about how much work is involved.

From far away, most complex problems seem simple to solve

Teams can commit to impossible deadlines by being overly optimistic and not thinking through the work

Few people realize the deadline is optimistic until it’s blown

Why do software projects fail?

Defects are injected early but discovered late.

Projects can address the wrong needs

Requirements can specify incorrect behavior

Design, architecture and code can be technically flawed

Test plans can miss functionality

The later these problems are found, the more likely they are to cause the project to fail

Why do software projects fail?

Programmers have poor habits – and they don’t feel accountable for their work.

Programmers don’t have good control of their source code

Code written by one person is often difficult for another person to understand

Programmers don’t test their code, which makes diagnosing and fixing bugs more expensive

The team does not have a good sense of the overall health of the project.

Why do software projects fail?

Managers try to test quality into the software.

Everyone assumes that the testers will catch all of the defects that were injected throughout the project.

When testers look for defects, managers tell them they are wasting time.

When testers find defects, programmers are antagonized because they feel that they are being personally criticized.

When testers miss defects, everyone blames them for not being perfect.

How can we make sure that our projects succeed?

Make sure all decisions are based on openly shared information

It’s important to create a culture of transparency, where everyone who needs information knows where to find it and is comfortable looking at it.

All project documents, schedules, estimates, plans and other work products should be shared with the entire team, managers, stakeholders, users and anyone else in the organization who wants them.

Major decisions that are made about the project should be well-supported and explained.

How can we make sure that our projects succeed?

Don’t second-guess your team members’ expertise

Managers need to trust team members.

Just because a manager has responsibility for a project’s success, it doesn’t mean that he’s more qualified to make decisions than the team members.

If you don’t have a good reason to veto an idea, don’t.

How can we make sure that our projects succeed?

Introduce software quality from the very beginning of the project

Review everything, test everything.

Use reviews to find defects – but don’t expect the review to be perfect.

Use reviews to gain a real commitment from the team.

It’s always faster in the long run to hold a review than it is to skip it.

How can we make sure that our projects succeed?

Don’t impose an artificial hierarchy on the project team

All software engineers were created equal.

A manager should not assume that programming

is more difficult or technical than design, testing or requirements engineering.

Managers should definitely not assume that the programmer is always right, or the tester is always raising false alarms.

How can we make sure that our projects succeed?

Remember that the fastest way through the project is to use good engineering practices

Managers and teams often want to cut important tasks – especially estimation, reviews, requirements gathering and testing.

If it were faster to build the software without these practices, we would never use them.

Every one of these practices is about saving time and increasing quality by planning well and finding defects early. Cutting them out will cost time and reduce quality.

1. Tại sao các dự án phần mềm thất bại (Why Software Projects Fail)

1.1 Bắt đầu lập trình trước khi hiểu rõ vấn đề

- Nhiều nhóm lập trình viên muốn thấy kết quả ngay, nên bắt đầu viết code mà chưa hiểu rõ yêu cầu hoặc phạm vi của dự án.

- Kết quả là họ có thể tạo ra phần mềm tốt về kỹ thuật nhưng lại không giải quyết đúng nhu cầu thực tế của người dùng.

- Khi dự án trở nên phức tạp hơn, nhóm thường bị sa lầy vì không có định hướng rõ ràng từ đầu.

1.2 Nhóm có kỳ vọng không thực tế về khối lượng công việc

- Từ góc nhìn ban đầu, mọi vấn đề dường như đơn giản.

- Các nhóm thường quá lạc quan và đánh giá thấp lượng công việc cần thiết, dẫn đến cam kết deadline không khả thi.

- Họ chỉ nhận ra điều đó sau khi deadline bị bỏ lỡ.

1.3 Lỗi được tạo ra sớm nhưng phát hiện muộn

- Sai sót có thể xảy ra ở bất kỳ giai đoạn nào: thu thập yêu cầu, thiết kế, lập trình, hoặc kiểm thử.

- Càng phát hiện lỗi muộn, chi phí khắc phục càng cao.

- Khi lỗi được phát hiện ở giai đoạn cuối, có thể phải thiết kế lại hoặc viết lại toàn bộ phần mềm, gây trễ hạn và tốn kém.

1.4 Lập trình viên có thói quen làm việc kém

- Không kiểm soát tốt mã nguồn (không dùng công cụ quản lý version).

- Mã do người này viết người khác khó hiểu.

- Không kiểm thử code của chính mình, làm việc sửa lỗi trở nên tốn kém.

- Không có cái nhìn tổng thể về sức khỏe dự án.

1.5 Quản lý cố “test chất lượng vào phần mềm”

- Nhiều nhà quản lý nghĩ rằng test kỹ lưỡng sẽ tự động tạo ra phần mềm chất lượng.

- Nhưng chất lượng phải được xây dựng xuyên suốt quy trình, chứ không thể “nhồi” vào ở giai đoạn kiểm thử.

- Khi tester phát hiện lỗi, lập trình viên cảm thấy bị chỉ trích. Khi tester bỏ sót lỗi, họ bị đổ lỗi — tạo ra môi trường làm việc tiêu cực.

2. Làm sao để đảm bảo dự án thành công (How Can We Make Sure Projects Succeed)

2.1 Đảm bảo mọi quyết định dựa trên thông tin minh bạch

- Tạo ra văn hoá minh bạch: mọi thành viên biết nơi tìm thông tin và được khuyến khích tiếp cận nó.

- Chia sẻ toàn bộ tài liệu, kế hoạch, ước lượng, và tiến độ với cả nhóm, nhà quản lý, người dùng, và bên liên quan.

- Mọi quyết định lớn phải có cơ sở rõ ràng và được giải thích công khai.

2.2 Không nghi ngờ năng lực của thành viên nhóm

- Quản lý phải tin tưởng chuyên môn của nhóm.

- Việc bạn là người chịu trách nhiệm cho dự án không có nghĩa là bạn hiểu kỹ thuật hơn lập trình viên hoặc tester.

- Nếu không có lý do chính đáng, đừng bác bỏ ý kiến chuyên môn của thành viên.

2.3 Đưa yếu tố chất lượng vào từ đầu dự án

- “Review everything, test everything.” – Hãy kiểm tra và rà soát mọi thứ.

- Tổ chức các buổi review tài liệu, thiết kế, mã nguồn để phát hiện lỗi sớm.

- Review không cần hoàn hảo, nhưng luôn tiết kiệm thời gian hơn việc bỏ qua và sửa lỗi sau.

2.4 Không áp đặt hệ thống cấp bậc giả tạo

- Tất cả kỹ sư phần mềm đều quan trọng: người phân tích yêu cầu, lập trình viên, tester, và người thiết kế.

- Lập trình viên không phải lúc nào cũng đúng, tester không phải lúc nào cũng “phàn nàn sai”.

- Một nhóm thành công là nhóm coi trọng mọi vai trò như nhau.

2.5 Ghi nhớ: cách nhanh nhất là làm đúng kỹ thuật

- Nhiều nhóm bỏ qua các bước như estimation, review, requirement gathering, testing để “tiết kiệm thời gian”.

- Nhưng nếu thật sự nhanh hơn, chúng ta đã không bao giờ cần làm những bước đó.

- Các quy trình tốt giúp phát hiện lỗi sớm, tăng chất lượng và tiết kiệm thời gian tổng thể.

3. Kết luận (Conclusion)

- Dự án phần mềm thất bại chủ yếu do quản lý và con người, không chỉ do kỹ thuật.

- Muốn thành công, hãy hiểu vấn đề trước khi code, ước lượng thực tế, và đảm bảo minh bạch trong giao tiếp.

- Đặt chất lượng, quy trình và con người làm trung tâm.