Applied Software Project Management

Reviews

When are reviews needed?

A review is any activity in which a work product is distributed to reviewers who examine it and give feedback.

- Reviews are useful not only for finding and eliminating defects, but also for gaining consensus among the project team, securing approval from stakeholders, and aiding in professional development for team members.

- Reviews help teams find defects soon after they are injected making them cost less to fix than they would cost if they were found in test.

- All work products in a software project should be either reviewed or tested.

• Software requirements specifications, schedules, design documents, code, test plans, test cases, and defect reports should all be reviewed.

Types of Review:

Inspections

Inspections are moderated meetings in which reviewers list all issues and defects they have found in the document and log them so that they can be addressed by the author. The goal of the inspection is to repair all of the defects so that everyone on the inspection team can approve the work product.

wCommonly inspected work products include software requirements specifications and test plans.

Types of Review:

Inspections

Running an inspection meeting:

- A work product is selected for review and a team is gathered for an inspection meeting to review the work product.

- A moderator is chosen to moderate the meeting.

- Each inspector prepares for the meeting by reading the work product and noting each defect.

- In an inspection, a defect is any part of the work product that will keep an inspector from approving it.

- Discussion is focused on each defect, and coming up with a specific resolution.

•	It’s the job of the inspection team to do more than just identify the problems; they must also come up with the solutions.

- The moderator compiles all of the defect resolutions into an inspection log

Inspection Log Example

Types of Review:

Deskchecks

A deskcheck is a simple review in which the author of a work product distributes it to one or more reviewers.

wThe author sends a copy of the work product to selected project team members. The team members read it, and then write up defects and comments to send back to the author.

Types of Review:

Deskchecks

Unlike an inspection, a deskcheck does not produce written logs which can be archived with the document for later reference.

Deskchecks can be used as predecessors to inspections.

wIn many cases, having an author of a work product pass his work to a peer for an informal review will significantly reduce the amount of effort involved in the inspection.

Types of Review:

Walkthroughs

A walkthrough is an informal way of presenting a technical document in a meeting.

- Unlike other kinds of reviews, the author runs the walkthrough: calling the meeting, inviting the reviewers, soliciting comments and ensuring that everyone present understands the work product.

- Walkthroughs are used when the author of a work product needs to take into account the perspective of someone who does not have the technical expertise to review the document.

- After the meeting, the author should follow up with individual attendees who may have had additional information or insights. The document should then be corrected to reflect any issues that were raised.

Types of Review:

Code Review

A code review is a special kind of inspection in which the team examines a sample of code and fixes any defects in it.

wIn a code review, a defect is a block of code which does not properly implement its requirements, which does not function as the programmer intended, or which is not incorrect but could be improved

• For example, it could be made more readable or its performance could be improved

Types of Review:

Code Review

- It’s important to review the code which is most likely to have defects. This will generally be the most complex, tricky or involved code.

- Good candidates for code review include:

  - A portion of the software that only one person has the expertise to maintain

  - Code that implements a highly abstract or tricky algorithm

  - An object, library or API that is particularly difficult to work with

  - Code written by someone who is inexperienced or has not written that kind of code before, or written in an unfamiliar language

  - Code which employs a new programming technique

  - An area of the code that will be especially catastrophic if there are defects

Types of Review: Pair Programming

Pair programming is a technique in which two programmers work simultaneously at a single computer and continuously review each others’ work.

Although many programmers were introduced to pair programming as a part of Extreme Programming, it is a practice that can be valuable in any development environment.

Pair programming improves the organization by ensuring that at least two programmers are able to maintain any piece of the software.

Types of Review:

Pair Programming

In pair programming, two programmers sit at one computer to write code. Generally, one programmer will take control and write code, while the other watches and advises.

- Some teams have found that pair programming works best for them if the pairs are constantly rotated; this helps diffuse the shared knowledge throughout the organization. Others prefer to pair a more junior person with a more senior for knowledge sharing.

The project manager should not try to force pair programming on the team; it helps to introduce the change slowly, and where it will meet the least resistance.

- It is difficult to implement pair programming in an organization where the programmers do not share the same nine-to-five (or tento-six) work schedule.

- Some people do not work well in pairs, and some pairs do not work well together.

1️⃣ Khi nào cần thực hiện đánh giá (When Are Reviews Needed)

- Review là mọi hoạt động mà trong đó một sản phẩm công việc (work product) được chia sẻ với người khác để họ xem xét và phản hồi.

- Review không chỉ giúp tìm và loại bỏ lỗi, mà còn giúp:

  - Tạo sự đồng thuận trong nhóm.

  - Nhận được phê duyệt từ stakeholder.

  - Trao đổi kiến thức và phát triển chuyên môn của các thành viên.

- Lợi ích lớn nhất: phát hiện lỗi sớm → chi phí sửa thấp.

- Trong một dự án phần mềm, mọi sản phẩm công việc nên được review hoặc test, ví dụ:

  - Tài liệu yêu cầu (SRS)

  - Lịch trình (Schedule)

  - Thiết kế (Design document)

  - Code

  - Test plan, test case

  - Báo cáo lỗi (Defect reports)

🟩 Tóm lại: Review = “kiểm tra chéo” để đảm bảo chất lượng và hiểu biết chung trong nhóm.

2️⃣ Các loại hình đánh giá (Types of Reviews)

A. Inspections (Kiểm tra chính thức)

- Là cuộc họp có điều phối (moderated meeting),
trong đó người tham gia liệt kê tất cả lỗi và vấn đề trong tài liệu được xem xét.

- Mục tiêu: sửa toàn bộ lỗi để tài liệu được nhóm phê duyệt.

- Các sản phẩm thường được inspection:

  - Tài liệu yêu cầu (SRS)

  - Kế hoạch kiểm thử (Test Plan)

Quy trình Inspection:

- Chọn tài liệu để review.

- Tập hợp nhóm review (3–6 người).

- Chọn Moderator (người điều phối) – giúp buổi họp hiệu quả.

- Mỗi thành viên đọc trước tài liệu và ghi chú lỗi.

- Trong buổi họp:

  - Chỉ tập trung liệt kê lỗi, không tranh cãi ai đúng.

  - Thảo luận cách sửa cụ thể cho từng lỗi.

- Moderator ghi lại tất cả lỗi và cách khắc phục trong Inspection Log (Nhật ký kiểm tra).

🟢 Mục tiêu: Sau buổi họp, tác giả sửa toàn bộ lỗi để tài liệu đạt chất lượng mong muốn.

B. Deskcheck (Kiểm tra bàn – cá nhân)

- Là dạng review đơn giản, không chính thức.

- Tác giả gửi tài liệu cho 1 hoặc vài người khác xem, họ đọc và phản hồi lại lỗi/nhận xét.

- Không cần họp, không có log chính thức.

- Deskcheck thường được thực hiện trước khi inspection để giảm lỗi dễ thấy.

🟩 Ví dụ:
Trước khi tổ chức inspection cho tài liệu SRS, tác giả gửi trước cho đồng nghiệp xem qua để “lọc” bớt lỗi nhỏ.

🟢 Ưu điểm: nhanh, tiết kiệm thời gian.
🟠 Nhược điểm: không có bằng chứng chính thức và dễ bỏ sót lỗi phức tạp.

C. Walkthrough (Trình bày hướng dẫn)

- Là buổi họp không chính thức, do chính tác giả tổ chức.

- Tác giả:

  - Giới thiệu tài liệu (design, test plan, code, v.v.)

  - Mời người khác tham gia.

  - Giải thích từng phần nội dung.

  - Ghi nhận nhận xét và câu hỏi.

- Walkthrough giúp người khác hiểu công việc của tác giả và phát hiện lỗi nhỏ.

- Thường được dùng khi:

  - Cần chia sẻ kiến thức với người không trực tiếp làm việc kỹ thuật.

  - Hoặc muốn phản hồi nhanh trước khi phát hành tài liệu chính thức.

📌 Sau buổi họp, tác giả nên chỉnh sửa lại tài liệu theo phản hồi nhận được.

D. Code Review (Đánh giá mã nguồn)

- Là dạng đặc biệt của inspection, tập trung vào mã nguồn chương trình (source code).

- Mục tiêu: phát hiện lỗi logic, hiệu năng, và cải thiện chất lượng code.

- Một defect trong code có thể là:

  - Vi phạm yêu cầu.

  - Không hoạt động như mong đợi.

  - Hoặc code “đúng” nhưng chưa tối ưu, khó hiểu, hoặc khó bảo trì.

Khi nào nên review code:

- Khi module đó:

  - Phức tạp hoặc quan trọng.

  - Chỉ có 1 người hiểu rõ (rủi ro cao nếu người đó nghỉ việc).

  - Dễ gây lỗi nghiêm trọng nếu sai.

  - Sử dụng kỹ thuật hoặc ngôn ngữ mới.

🟢 Tóm lại: Code Review giúp phát hiện lỗi sớm, tăng khả năng bảo trì và chia sẻ kiến thức.

E. Pair Programming (Lập trình đôi)

- Là kỹ thuật trong đó 2 lập trình viên cùng làm việc trên 1 máy tính.

  - Một người viết code (driver).

  - Người kia quan sát, góp ý, và kiểm tra logic (observer/navigator).

- Họ liên tục xem xét và phản hồi lẫn nhau.

- Pair Programming phổ biến trong Extreme Programming (XP),
nhưng cũng có thể áp dụng trong bất kỳ môi trường nào.

Lợi ích:

- Giảm lỗi logic, tăng tốc độ phát hiện vấn đề.

- Giúp lan tỏa kiến thức trong nhóm.

- Mỗi phần code có ít nhất 2 người hiểu.

Khó khăn:

- Cần tương tác liên tục → khó áp dụng nếu làm việc giờ khác nhau.

- Không phải cặp nào cũng làm việc ăn ý.

- Phải chọn người hợp tính, bổ trợ kỹ năng cho nhau.

3️⃣ So sánh các loại review (Comparison Table)

| Loại Review | Chính thức | Ai tổ chức | Có họp không | Có ghi log | Mục tiêu chính |
| --- | --- | --- | --- | --- | --- |
| Inspection | ✅ Có | Moderator | ✅ Có | ✅ Có | Phát hiện & sửa lỗi kỹ thuật |
| Deskcheck | ❌ Không | Tác giả | ❌ Không | ❌ Không | Phản hồi nhanh, sửa lỗi nhỏ |
| Walkthrough | ❌ Không | Tác giả | ✅ Có | ❌ Không | Giải thích & chia sẻ tài liệu |
| Code Review | ✅ Có thể | Nhóm dev | ✅ Có | ✅ Có | Phát hiện lỗi trong mã nguồn |
| Pair Programming | ❌ Không | Hai dev cùng thực hiện | ❌ Không | ❌ Không | Kiểm tra liên tục khi code |