# Applied Software Project Management

Software Project Planning

Who needs software?

Most software is built in organizations for people with specific needs.

A stakeholder is an anyone who has an interest

(or stake) in the software being completed

A user is someone who will need to use the software to perform tasks.

Sometimes stakeholders will be users; but often the stakeholder will not use the software.

• For example, a senior manager (like a CEO or CTO in a company) will usually have a stake in the software that is built (since it affects the bottom line), even if she won’t ever use it.

Who builds software?

Software is typically built by a team of software engineers, which includes:

Business analysts or requirements analysts who talk to users and stakeholders, plan the behavior of software and write software requirements

Designers and architects who plan the technical solution

Programmers who write the code

Testers who verify that the software meets its requirements and behaves as expected

# Project Management

The project manager plans and guides the software project

The project manager is responsible for identifying the users and stakeholders and determining their needs

The project manager coordinates the team, ensuring that each task has an appropriate software engineer assigned and that each engineer has sufficient knowledge to perform it

To do this well, the project manager must be familiar with every aspect of software engineering

# Identifying Needs

The project manager drives the scope of the project.

The project manager should identify and talk to the main stakeholder

The effective way to show stakeholders that their needs are understood and that those specific needs will be addressed is with a vision and scope document

# Vision and Scope Document

A typical vision and scope document follows an outline like this one:

- Problem Statement

  - Project background

  - Stakeholders

  - Users

  - Risks

  - Assumptions

- Vision of the Solution

  - Vision statement

  - List of features

  - Scope of phased release (optional)

  - Features that will not be developed

# Project Plan

The project plan defines the work that will be done on the project and who will do it. It consists of:

- A statement of work (SOW) that describes all work products that will be produced and a list of people who will perform that work

- A resource list that contains a list of all resources that will be needed for the product and their availability

- A work breakdown structure and a set of estimates

- A project schedule

- A risk plan that identifies any risks that might be encountered and indicates how those risks would be handled should they occur

# Statement of Work

The statement of work (SOW) is a detailed description of all of the work products which will be created over the course of the project. It includes:

A list of features that will be developed

A description of each intermediate deliverable or work product that will be built.

The estimated effort involved for each work product to be delivered

# Resource List

The project plan should contain a list of all resources that will be used on the project.

A resource is a person, hardware, room or anything else that is necessary for the project but limited in its availability

The resource list should give each resource a name, a brief one-line description, and list the availability and cost (if applicable) of the resource

## Estimates and Project Schedule

The project plan should also include estimates and a project schedule:

- A work breakdown structure (WBS) is defined. This is a list of tasks which, if performed, will generate all of the work products needed to build the software.

- An estimate of the effort required for each task in the WBS is generated.

- A project schedule is created by assigning resources and determining the calendar time required for each task.

Estimates and project schedules will be discussed in detail in later slides.

# Risk Plan

A risk plan is a list of all risks that threaten the project, along with a plan to mitigate some or all of those risks.

The project manager selects team members to participate in a risk planning session:

- The team members brainstorm potential risks

- The probability and impact of each risk is estimated

- A risk plan is constructed

# Risk Plan Example

1️⃣ Ai cần phần mềm (Who Needs Software)

- Phần lớn phần mềm được xây dựng trong tổ chức để phục vụ những người có nhu cầu cụ thể.

- Stakeholder (Bên liên quan): bất kỳ ai có lợi ích (hoặc rủi ro) liên quan đến việc hoàn thành phần mềm.
→ Ví dụ: nhà đầu tư, quản lý, khách hàng, trưởng phòng kinh doanh.

- User (Người dùng): người trực tiếp sử dụng phần mềm để thực hiện công việc.

- Đôi khi stakeholder cũng là user, nhưng thường thì không phải.
→ Ví dụ: Giám đốc điều hành (CEO) quan tâm đến lợi nhuận, nhưng không trực tiếp dùng phần mềm.

2️⃣ Ai xây dựng phần mềm (Who Builds Software)

Một dự án phần mềm thường được thực hiện bởi một nhóm kỹ sư phần mềm gồm nhiều vai trò:

- Business Analyst / Requirements Analyst
→ Trao đổi với người dùng và bên liên quan để xác định hành vi phần mềm, viết tài liệu yêu cầu.

- Designers / Architects
→ Lên kế hoạch giải pháp kỹ thuật: cấu trúc hệ thống, kiến trúc phần mềm.

- Programmers (Lập trình viên)
→ Viết mã nguồn để hiện thực yêu cầu.

- Testers (Kiểm thử viên)
→ Đảm bảo phần mềm đáp ứng yêu cầu và hoạt động đúng như mong đợi.

3️⃣ Quản lý dự án (Project Management)

- Người quản lý dự án (Project Manager) chịu trách nhiệm lập kế hoạch và điều phối toàn bộ quá trình phát triển.

- Công việc chính:

  - Xác định người dùng và bên liên quan, hiểu nhu cầu của họ.

  - Phân công nhiệm vụ cho từng kỹ sư phù hợp với kỹ năng.

  - Đảm bảo mọi người hiểu rõ công việc của mình.

- Quản lý giỏi phải hiểu tổng thể quy trình kỹ thuật phần mềm, không chỉ về con người.

4️⃣ Xác định nhu cầu (Identifying Needs)

- Project Manager là người định hướng phạm vi (scope) của dự án.

- Bước đầu tiên là nói chuyện trực tiếp với stakeholder chính để hiểu mục tiêu thật sự.

- Cách hiệu quả nhất để chứng minh bạn hiểu họ là soạn “Vision and Scope Document.”

5️⃣ Tài liệu Vision and Scope (Vision and Scope Document)

Một bản Vision & Scope chuẩn thường bao gồm:

1. Problem Statement – Mô tả vấn đề

- a) Bối cảnh dự án (Project background)

- b) Các bên liên quan (Stakeholders)

- c) Người dùng (Users)

- d) Rủi ro (Risks)

- e) Giả định (Assumptions)

2. Vision of the Solution – Tầm nhìn giải pháp

- a) Vision statement – mô tả ngắn gọn sản phẩm sẽ đạt được.

- b) Danh sách các tính năng (List of features).

- c) Phạm vi từng giai đoạn (Scope of phased release – nếu có).

- d) Các tính năng sẽ không phát triển (Out-of-scope features).

👉 Tài liệu này là cam kết giữa nhóm phát triển và stakeholder – đảm bảo hai bên hiểu giống nhau về mục tiêu và giới hạn của dự án.

6️⃣ Kế hoạch dự án (Project Plan)

Kế hoạch dự án định nghĩa công việc sẽ được làm, ai sẽ làm và khi nào.
Nó thường bao gồm 5 thành phần chính:

- Statement of Work (SOW)
→ Mô tả chi tiết tất cả sản phẩm cần tạo ra trong suốt dự án, gồm:

  - Danh sách các tính năng sẽ được phát triển

  - Mô tả từng sản phẩm trung gian (intermediate deliverable)

  - Ước lượng công sức (effort estimate) cho từng đầu việc

- Resource List
→ Danh sách tất cả nguồn lực cần thiết:

  - Nhân sự, phần cứng, phòng ban, thiết bị…

  - Ghi rõ: tên, mô tả, thời gian sẵn có, chi phí (nếu có).

- Work Breakdown Structure (WBS)
→ Danh sách chi tiết các nhiệm vụ cần làm để tạo ra toàn bộ sản phẩm phần mềm.
→ Là cơ sở để ước lượng công việc và thời gian.

- Project Schedule (Lịch trình dự án)
→ Sau khi có WBS và estimate, quản lý sẽ:

  - Gán tài nguyên (resources)

  - Tính thời gian hoàn thành từng nhiệm vụ

  - Lập lịch làm việc thực tế theo ngày/tháng.

- Risk Plan (Kế hoạch rủi ro)
→ Liệt kê tất cả các rủi ro có thể đe dọa dự án và kế hoạch xử lý khi xảy ra.

7️⃣ Kế hoạch rủi ro (Risk Plan)

- Quản lý dự án chọn một nhóm thành viên có kinh nghiệm để tham gia buổi lập kế hoạch rủi ro.

- Các bước thực hiện:

  - Cả nhóm brainstorm tất cả rủi ro tiềm ẩn.

  - Ước lượng xác suất (probability) và mức ảnh hưởng (impact) cho từng rủi ro.

  - Lập Risk Plan mô tả cách giảm thiểu hoặc xử lý rủi ro đó.

✅ Ví dụ:

- Rủi ro: Nhân sự chủ chốt nghỉ việc.
→ Giải pháp: Ghi chú quy trình, backup kiến thức, có kế hoạch tuyển người thay.

- Rủi ro: Client đổi yêu cầu.
→ Giải pháp: Thiết lập quy trình kiểm soát thay đổi (change control).