# Applied Software Project Management

Project Schedules

What is a project schedule?

The project schedule is a calendar that links the tasks to be done with the resources that will do them.

Before a project schedule can be created, the project manager must have a work breakdown structure (WBS) and estimates.

The schedule is part of the project plan.

Scheduling concepts:

Effort vs. Duration

Effort represents the work required to perform a task.

- Effort is measured in person-hours (or person-days, personweeks, etc.)

- It represents the total number of hours that each person spent working on the task.

Duration is amount of time that elapses between the time the task is started and the time it is completed.

- Duration is measured in hours (or days, weeks, etc.)

- It does not take into account the number of people performing the task

## Scheduling concepts: Slack and Overhead

Slack is the amount of time which any of the tasks can be delayed without causing the due date of the final task in the sequence to be delayed as well.

- A tight schedule has very little slack; a delay in any task will cause a delay in the due date

- Parkinson’s Law: “Work expands so as to fill the time available for its completion.”

Overhead is any effort that does not go to the core activities of the task but is still required in order for the people to perform it— a sort of “real world” cost of actually doing the work.

- Two people performing a task will require more effort than one person doing the same task

- Assigning two people to the task requires more effort, but the task has a shorter duration

# Building the project schedule

Allocate resources

For each task in the WBS, one or more resources must be assigned

Choose person or people for each task based on qualifications, familiarity and availability

Take overhead into account when calculating the duration of each task

# Building the project schedule

Identify dependencies

A task has a dependency if it involves an activity, resource or work product which is subsequently required by another task

Tasks may have dependencies because they require the same resource

# Building the project schedule

Identify dependencies (continued)

- Every dependency has a predecessor, or a task that must be begun, in progress, or completed, for another task to begin

- Identify the type of predecessor for each dependency

# Building the project schedule

Create the schedule

Most project schedules are represented using a Gantt chart

The Gantt chart shows tasks, dependencies and milestones using different shapes

# Building the project schedule

Reconcile the schedule with the organization’s needs

Once resources are allocated to each task, a final date can be calculated

If this date is unacceptable, the project plan must change

Either additional resources must be allocated to the project or the scope must be cut down

Brooks’ Law: “Nine women cannot have a baby in one month.”

• In other words, some tasks can only be done by one person, no matter how critical they are.

# Building the project schedule

Add review meetings to the schedule

Progress reviews are meetings held regularly to check the progress of a project versus it's scheduled progress.

Milestone reviews are meetings which the project manager schedules in advance to coincide with project events.

• The most common way for project managers to handle milestone reviews is to schedule them to occur after the last task in a project phase (such as the end of design or programming).

# Building the project schedule

Optimize the schedule

- The critical path is the sequence of tasks that represent the minimum time required to complete the project.

  - If a task is only on the critical path when delaying that task will delay the project.

  - Allocating resources to tasks on the critical path will reduce the project schedule; allocating them to other tasks will have less effect.

- A resource is over-allocated if more than 100% allocated to multiple tasks simultaneously

  - If any resource is over-allocated, it means that there is a dependency between two tasks which was not discovered.

  - When this happens, the schedule is guaranteed to be inaccurate. Find and fix over-allocated resources.

# Don’t abuse buffers

A buffer is a task added to the schedule with no specific purpose except to account for unexpected delays.

- This practice involves either adding extra tasks or padding existing tasks at strategic points in the schedule where overruns are “expected”.

- Buffers can be useful:

  - On a year-long project, every programmer will take two weeks of vacation

  - Buffers can be used to account for this known delay  Buffers are often abused

  - The idea that overruns are expected means that there is an implicit assumption that the estimate is incorrect.

  - Buffers should not be used to add time to compensate for an inaccurate estimate.

# Project metrics

The baseline is the version of the schedule that has been approved

The schedule will change based on the actual work done by the project team.

When the deadline of the revised schedule is later than that of the baseline, the project has slipped.  Variance is the difference between the estimated effort in the baseline and the actual effort performed by the team.

# Project metrics

Earned value management tracks the project by considering effort “earned” against a

budget only after it has actually been performed

The budgeted cost for work scheduled (BCWS) is the estimated effort of the actual tasks that appear on the schedule to date.

The actual cost of work performed (ACWP) is the effort spent on the tasks in the schedule that have actually been completed by the development team members.

Variance = BCWS – ACWP

# Project metrics

The cost performance index is used to compare projects with each other or to compare phases within a project

- CPI is calculated by dividing BCWS / ACWP (budgeted cost for work scheduled/actual cost for work performed) and multiplying by 100 to express it as a percentage.

- A CPI of 100% means that the estimated cost was exactly right and the project came in exactly on budget.

- A CPI under 100%, the work cost less effort than planned; a CPI greater than 100% means that the estimate was not adequate for the work involved.

• For example, if the programming tasks took twice as long as estimated but every other type of task in the project took less time than estimated, the total variance for the project might still be low. However, the problem can still be pinpointed by calculating the CPI for each phase of development.

1️⃣ Lịch trình dự án là gì (What is a Project Schedule)

- Lịch trình dự án (Project Schedule) là bản kế hoạch thời gian,
thể hiện công việc nào được thực hiện khi nào, bởi ai.

- Nó liên kết giữa “nhiệm vụ” (tasks) trong Work Breakdown Structure (WBS)
với “nguồn lực” (resources) sẽ thực hiện chúng.

- Trước khi lập lịch, quản lý phải có WBS và ước lượng (estimates).

🟩 Tóm lại:

Lịch trình là “bản đồ thời gian” của dự án – giúp biết ai làm gì, trong bao lâu, và khi nào xong.

2️⃣ Khái niệm cơ bản: Effort và Duration (Scheduling Concepts: Effort vs. Duration)

- Effort (Công sức): tổng số thời gian con người làm việc cho một nhiệm vụ.
→ Đo bằng giờ-người, ngày-người, hoặc tuần-người.
→ Ví dụ: 2 người làm trong 3 ngày = 6 person-days.

- Duration (Thời lượng): khoảng thời gian từ khi bắt đầu đến khi hoàn thành nhiệm vụ.
→ Đo bằng giờ, ngày, hoặc tuần.
→ Không tính số người tham gia.

📌 Ví dụ:
Nếu 1 người làm trong 4 ngày thì Effort = 4 ngày, Duration = 4 ngày.
Nếu 2 người cùng làm thì Effort = 8 ngày, Duration = 2 ngày.

3️⃣ Slack và Overhead (Scheduling Concepts: Slack and Overhead)

Slack (Độ trễ cho phép):

- Là thời gian có thể trì hoãn một nhiệm vụ mà không làm chậm toàn bộ dự án.

- Lịch trình có slack thấp nghĩa là: nếu một task trễ, cả dự án trễ.

“A tight schedule has little slack.”
(Lịch trình chặt chẽ có rất ít thời gian trễ cho phép.)

Overhead (Chi phí gián tiếp):

- Là công sức ngoài nhiệm vụ chính nhưng vẫn cần để hoàn thành công việc.

- Ví dụ: họp, báo cáo, chờ đợi tài nguyên, thời gian đào tạo.

📌 2 người cùng làm một nhiệm vụ không có nghĩa thời lượng giảm 50%,
vì overhead tăng (trao đổi, phối hợp, kiểm tra,…).

4️⃣ Các bước xây dựng lịch trình (Building the Project Schedule)

Bước 1 – Phân bổ nguồn lực (Allocate Resources)

- Gán người/phòng ban/thiết bị phù hợp cho từng nhiệm vụ trong WBS.

- Cân nhắc trình độ, kinh nghiệm và mức độ sẵn sàng của mỗi người.

- Tính thêm overhead khi có nhiều người cùng tham gia.

Bước 2 – Xác định phụ thuộc (Identify Dependencies)

- Một nhiệm vụ có phụ thuộc (dependency) nếu nó phải chờ nhiệm vụ khác hoàn thành hoặc bắt đầu trước.

- Có 4 loại phụ thuộc phổ biến:

  - Finish-to-Start (FS): Task B bắt đầu khi Task A hoàn thành.

  - Start-to-Start (SS): Task B bắt đầu khi Task A bắt đầu.

  - Finish-to-Finish (FF): Task B kết thúc khi Task A kết thúc.

  - Start-to-Finish (SF): (hiếm gặp) Task B kết thúc khi Task A bắt đầu.

🟩 Tóm lại: Xác định phụ thuộc giúp lịch trình logic, không chồng chéo hoặc thiếu bước.

Bước 3 – Tạo lịch (Create the Schedule)

- Dùng công cụ như Gantt Chart để biểu diễn nhiệm vụ, thời lượng và mốc thời gian.

- Gantt Chart thể hiện:

  - Nhiệm vụ (tasks)

  - Phụ thuộc (dependencies)

  - Mốc (milestones)

📊 Mẹo:
Mốc (Milestone) = một điểm quan trọng (ví dụ: “Hoàn tất thiết kế” hoặc “Bắt đầu kiểm thử”).
Không có thời lượng, chỉ đánh dấu thời điểm kiểm tra tiến độ.

Bước 4 – Cân đối với yêu cầu tổ chức (Reconcile the Schedule with Organizational Needs)

- Sau khi có lịch sơ bộ, PM tính ngày hoàn thành dự kiến.

- Nếu ngày đó không phù hợp với yêu cầu tổ chức, có 3 lựa chọn:

  - Cắt giảm phạm vi (scope).

  - Tăng thêm nguồn lực (resources).

  - Chấp nhận kéo dài deadline.

“Brooks’ Law”: Nine women cannot have a baby in one month.
(9 người phụ nữ không thể sinh con trong 1 tháng.)
→ Có những công việc không thể chia nhỏ để làm nhanh hơn.

Bước 5 – Thêm các buổi đánh giá (Add Review Meetings)

- Thêm Progress Reviews để kiểm tra tiến độ thực tế so với lịch.

- Thêm Milestone Reviews tại các điểm kết thúc giai đoạn:

  - Sau khi hoàn thành thiết kế.

  - Sau khi hoàn thành lập trình.

  - Sau khi kết thúc kiểm thử.

🟩 Ý nghĩa: giúp phát hiện trễ hạn sớm, không đợi đến cuối dự án mới biết.

Bước 6 – Tối ưu hóa lịch (Optimize the Schedule)

- Critical Path (Đường găng):
Là chuỗi nhiệm vụ quyết định thời gian hoàn thành ngắn nhất của dự án.
→ Nếu một nhiệm vụ trên đường găng trễ → toàn bộ dự án trễ.

- Cách rút ngắn lịch trình:

  - Tăng nguồn lực vào các nhiệm vụ nằm trên critical path.

  - Giảm phạm vi.

  - Không thêm người vào các task không nằm trên đường găng.

- Overallocation (Phân bổ quá mức):

  - Xảy ra khi một người được giao >100% công việc cùng lúc.

  - Dấu hiệu: trùng nhiệm vụ, lịch ảo.

  - Giải pháp: chia nhỏ công việc hoặc thay đổi thứ tự thực hiện.

5️⃣ Không lạm dụng buffer (Don’t Abuse Buffers)

- Buffer = khoảng đệm thời gian thêm vào lịch trình để phòng rủi ro.

- Dùng đúng: hợp lý (ví dụ: tính cả thời gian nghỉ phép).

- Dùng sai: “chèn thêm thời gian” vì không tin vào ước lượng.

🟩 Tóm lại:

Buffer dùng để xử lý rủi ro thực tế, không phải để che giấu ước lượng sai.

6️⃣ Chỉ số và đo lường tiến độ (Project Metrics)

Baseline (Đường cơ sở):

- Là phiên bản lịch trình được phê duyệt chính thức.

- Khi thực tế khác so với baseline → dự án đã trượt tiến độ (slipped).

Variance (Độ sai lệch):

- Là hiệu giữa effort thực tế và effort ước lượng trong baseline.

- Dùng để đo mức độ chính xác của kế hoạch.

Earned Value Management (EVM):

Theo dõi dự án bằng cách so sánh effort và chi phí theo thời gian.

- BCWS (Budgeted Cost for Work Scheduled):
Chi phí dự kiến cho phần công việc đáng ra phải hoàn thành tới thời điểm hiện tại.

- ACWP (Actual Cost of Work Performed):
Chi phí thực tế cho phần công việc đã hoàn thành.

- Variance = BCWS – ACWP
→ Nếu âm → chi phí thực tế cao hơn dự kiến.

CPI (Cost Performance Index):

- CPI = (BCWS / ACWP) × 100%

- CPI = 100%: đúng như kế hoạch.

- CPI > 100%: tốn ít hơn dự kiến (tốt).

- CPI < 100%: vượt chi phí (xấu).

📌 Ví dụ:
Nếu giai đoạn “lập trình” CPI = 80%, nghĩa là mất nhiều công sức hơn 20% so với dự kiến.