SOFTWARE PROJECT MANAGEMENT

Lab 7: Sprint Retrospective & Process Improvement

Group: 14 Members:

Trịnh Văn Đức – ITITIU21182

Mai Quốc Bình – ITDSIU21077

Lưu Trung Đức – ITDSIU20003

- Sprint 1 Metrics:

  - Sprint 1 Story Data:

| ID | Story | Pts | Status | Completion Day |
| --- | --- | --- | --- | --- |
| US-01 | Registration | 3 | Done | Day 2 |
| US-02 | Login/Session | 2 | Done | Day 3 |
| US-10 | Enforce HTTPS/JWT | 1 | Done | Day 5 |
| US-03 | Core Task Mgmt | 5 | Done | Day 6 |
| US-05 | Comment system | 3 | Done | Day 7 |
| US-08 | Usability/Responsive | 5 | Done | Day 8 |
| US-04 | Dashboard overview | 8 | Done | Day 9 |

  - Computed Metrics:

- Planned points: 27 points.

- Completed points: 27 points (All stories marked "Done" ).

- Completion distribution:

- First Half (Days 1–5): US-01, US-02, US-10.

  - 3 + 2 + 1 = 6 points.

- Second Half (Days 6–10): US-03, US-05, US-08, US-04.

  - 5 + 3 + 5 + 8 = 21 points.

- Average Completion Day:

AvgCompletionDay = (2+3+5+6+7+8+9) / 7 = 40 / 7 = 5.71

  - Interpretation of Metrics:

- Heavy Back-loading: There is a significant imbalance in the workflow. Only 6 points were finished in the first half, while 21 points (nearly 78% of the workload) were finished in the second half. This suggests a "mini-waterfall" pattern within the Sprint.

- Dependency Bottleneck: The Average Completion Day is approximately Day 6. This perfectly correlates with the completion of US-03 (Core Task Mgmt) on Day 6. Since US-05, US-08, and US-04 depended on US-03, they were blocked until the second half of the Sprint.

- Risk of Large Stories: US-04 (8 points) was completed very late on Day 9. If any issues had arisen during testing for this story, the team would have failed to deliver a large portion (30%) of the Sprint value.

- Capacity vs. Velocity: The team estimated a capacity of 24 points but successfully delivered 27 points. This indicates the team under-estimated their actual velocity slightly, but it provided a safe buffer.

- Testing Pressure: Completing 21 points in the last 4 days likely put immense pressure on verification and testing. This increases the risk of hidden bugs making it into the release.

- Retrospective (Keep / Improve / Try):

Based on the metrics above, the team brainstormed the following:

| Keep | Improve | Try |
| --- | --- | --- |
| Commitment Accuracy: We successfully delivered the full scope (27 points) and finished 1 day early (Day 9). | Late Integration: Waiting until Day 6 to finish the core dependency (US-03) caused a rush at the end. | Split Large Stories: Break down any story larger than 5 points (like US-04) into smaller chunks during planning. |
| Dependency Mapping: We correctly identified dependencies in Lab 4; US-03 was indeed the critical path | Work Balance: The "6 vs 21" point distribution is unhealthy and risky for Quality Assurance. | Swarming: Assign 2 developers to work together on critical blocking stories (like US-03) to finish them by Day 3. |
| Buffer Management: Finishing on Day 9 gave us a safe buffer for the final review. | Code Review Speed: Dependent tasks sat idle while waiting for the main task to pass review/testing. | Mid-Sprint Check: A quick review on Day 5 to check if we have completed at least 40% of the points. |

- Improvement Backlog for Sprint 2:

  - We selected the top 3 actionable improvements:

| ID | Improvement Item | Reason / Target | Owner |
| --- | --- | --- | --- |
| IM-01 | Enforce Story Point Cap (Max 5) | US-04 (8 pts) finished Day 9. Target: Split all 8+ point stories to ensure smoother flow and earlier completion. | Trịnh Văn Đức |
| IM-02 | "Swarm" on Core Dependencies | US-03 blocked 16 points of work until Day 6. Target: Clear critical dependencies by Day 3 or 4. | Mai Quốc Bình |
| IM-03 | Day-5 Progress Check | The 6 vs 21 distribution is risky. Target: Ensure "Completed Points" > 10 by Day 5. | Lưu Trung Đức |

  - Integration into Sprint 2:

- Planning Phase: During Sprint 2 planning, we will review the backlog. Any item estimated at 8 or 13 points will be explicitly split into smaller user stories (implementing IM-01).

- Daily Execution: We will assign the two most experienced members to pair-program on the most critical dependency story starting Day 1, ensuring it is Done ASAP to unlock work for others (implementing IM-02).

- Process Check: We will add a calendar invite for a 15-minute "metrics check" on the morning of Day 5 to compare actual progress against the burndown ideal line (implementing IM-03).

- Reflection:

  - Metrics vs. Feeling: The team felt the Sprint went "smoothly" because we finished on time. However, the metrics (Distribution & Avg Day) revealed a dangerous bottleneck where most work piled up at the end.

  - Managing Dependencies: We learned that simply knowing dependencies isn't enough. We actively need to prioritize the "blocking" tasks (like US-03) to unblock the rest of the Sprint board.

  - Velocity Confidence: Having delivered 27 points successfully, we are more confident in our velocity. We can likely commit to ~26-28 points in Sprint 2 without over-stressing, provided we balance the flow better.

  - The "8-Point" Risk: We realized that 8-point stories (like the Dashboard) are difficult to track. They stay "In Progress" for too long (Day 1 to Day 9), obscuring real progress. Splitting them is essential for transparency.